## Sheet1
Planning a Scout Outing | Work with the Adults, and Patrol Leaders Throughout the Process Anything in Red is to be Done at the Troop Meetings
Four Weeks Before the Camp-Out | Comments | Done | Initial
Go Over Roses and Thorns From the Last Campout
Make Changes as Needed
Get a Preliminary Count on Who is Coming From Each Patrol Leader
Check With Adults on What is Already Planned
What Advancements, Scout Skills & Merit Badges Can be Worked on?
If Newer Scouts are Coming Consider What They Need for Achievements
What Can the Newer Scouts Work on and Get Done on This Outing?
What Can the Older Scouts Teach the New Scouts?
What Skills / Merit Badges Can Older Scouts Work On?
What Equipment Will be Needed for All of This?
Where Will We Get This Equipment?
Three Weeks Before the Camp-Out | Comments | Done | Initial
Get an Updated Count on Who is Coming From Each Patrol Leader
Write Out the Advancements, Scout Skills & Merit Badges That Will be Worked on
What Will the Older Scouts Teach the New Scouts?
What Skills / Merit Badges Will Older Scouts Work On?
What Equipment Will be Needed for All of This?
Notify SM / QM of Equipment Needs
Go Over Proper Clothing and Gear Needed for the Campout (i.e. Winter Wear, Etc…)
Patrols Begin Making Tentative Forms:
Rosters - Make Tentative List
Get Tentative Rosters to Adults to Begin Making Drive Charts
Duty Rosters - Remember to Consider What Advancements New Scouts Need
Tenting - Pair Up Newer and Older Scouts
Daily Planner - Put Times to Activities
Menu Planner
Think About TIME Involved in Cooking, Cleaning, Etc… as You Make Plans
Bring Recipes for Next Week
What Cooking Equipment will be Needed for the Meals Planned?
Be Sure to Let Quartermaster Know of the Needs
Two Weeks Before the Camp-Out | Comments | Done | Initial
Get an FINAL Count on Who is Coming From Each Patrol Leader
Finalize the Advancements, Scout Skills & Merit Badges That Will be Worked on
Finalize What the Older Scouts Teach the New Scouts
Finalize Skills / Merit Badges Older Scouts Will Work On
Finalize Equipment That Will be Needed for All of This
Notify SM / QM of Equipment Needs
Remind of Proper Clothing and Gear Needed for the Campout (i.e. Winter Wear, Etc…)
Patrols Finalize Making Forms:
Rosters
Get Final Rosters to Adults to Make Drive Charts
Finalize Duty Rosters - Consider What Advancements New Scouts Need
Finalize Tenting - Pair Up Newer and Older Scouts
Finalize Daily Planner - Put Times to Activities
Finalize Menu Planner - Go Over Recipes & Tell Quartermaster Equipment Needs
Think About TIME Involved in Cooking, Cleaning, Etc…
What Cooking Equipment will be Needed for the Meals Planned?
Be Sure to Get Paper Towels and Tin Foil
Be Sure to Let Quartermaster Know of the Needs
Elect a Grubmaster
One Week Before the Camp-Out | Comments | Done | Initial
Be Sure Older Scouts Know What They Will be Teaching
Be Sure Any Cooking / Training Equipment Needed is on Trailer
Check with Quartermaster
Remind of Proper Clothing and Gear Needed for the Campout (i.e. Winter Wear, Etc…)
Go Over Duty Rosters, Tenting, Daily Planner, Menu
Make Sure Recipes are Printed
Get Food Money to Grubmaster
Get Coolers from Quartermaster to Grubmasters
If PL or APL will Not be There - Substitues Must be Chosen for This Campout
Wednesday Before Camp-Out | Comments | Done | Initial
Check that Grubmaster is Getting the Food
Confirm that Activities Planned Will be Done
Day of the Campout | Comments | Done | Initial
Shakedown - Be Sure Dress Uniform / Boots / Water / Rain Gear
Check Off That All Who Said They Were Coming are There
Reassign Tent Mates if Necessary
Be Sure Food is There
Gather Patrol Together for Adults to Count (Keep them Quiet and in Line)